## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Jhitka PWSS in Binpur-1Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-III | ORD/000090/2021-2022 | 76/JSD | 25/06/2021 | 09/07/2021 | RADIANT | 1.89 | 1.71 | 90.65 | 1
2 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Jhitka PWSS in Binpur-1Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/000007/2022-2023 |  | 02/08/2022 | 02/08/2022 | RADIANT | 1.71 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000283/2020-2021 | 1582/MD | 11/12/2020 | 09/06/2021 | RAMENDRA NATH KAR | 15.06 | 0 | 0 | 80
4 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | Relaying of distribution pipe line (part)(Phase-I) of Jitka pipe water supply scheme to accommodate FHTC in Binpur-I Block under Jhargram Sub-Division within Jhargram Division P.H.E Dte. |  | Junior Engineer-III | ORD/000094/2022-2023 | 458/JHD | 11/11/2022 | 10/01/2023 | RAMENDRA NATH KAR | 7.77 | 7.77 | 100 | 0
5 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | New service connection |  |  | BILL/00644/2023-2024 | 26/JMD | 17/10/2023 | 17/10/2023 | WBSEDCL | 5.63 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | Restoration work for laying pipeline along the Kaiaberia-Pirakata-Dhansole-Lalgarh road for Jhitka Water Supply Scheme under Jhargram Division, PHE Dte. |  |  | BILL/00175/2022-2023 | BP-2022-23-177 | 15/03/2023 | 15/03/2023 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 1.46 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | Repair, renovation and painting of 2 nos Pump houses and 2 nos boundary walls for Jitka w/s scheme at Binpur-I block under Jhargram Sub-division within Jhargram Division, PHE Dte. . (2nd Call) [Ref. eNIT 03 OF AE/JSD OF 2024-2025, SL No. 01] | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000209/2024-2025 | 1105/JSD | 04/12/2024 | 18/12/2024 | SUPRAKASH MONDAL | 4.01 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories for additional T/Well at head work site as part of augmentation of Jhitka W/S scheme under Jhargram Mechanical Division, PHE. Dte. in the dist. of Jhargram. | Assistant Engineer |  | ORD/000291/2023-2024 | 2516/JMD | 25/08/2023 | 24/09/2023 | SHOVAN KUMAR DAS | 9.41 | 9.36 | 99.49 | 80
9 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10483 | Augmentation | Excess quotation payment for Jhitka-1 ,Binpur-1. |  |  | BILL/01315/2023-2024 | 66/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 0.93 | 0 | 0 | 0
Total | [13 empty] | 47.87 | 18.84 | 39.36