## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10489 | Augmentation | Retrofitting to accommodate FHTC under JJM in Ragra PWSS of Sankrail Block under Jhargram Division, PHE Dte. |  |  | ORD/000199/2020-2021 | 1402/MD | 26/11/2020 | 25/05/2021 | ASIS KUMAR SARANGI | 60.82 | 9.67 | 15.89 | 1
2 | JHARGRAM |  | Midnapore Division | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10489 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rogra PWSS in Sankrail Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/000306/2022-2023 | BP-2022-23-96 | 04/06/2022 | 04/06/2022 | RADIANT | 1.86 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10489 | Augmentation | Construction of 200 cum OHR, Interconnection pipe line with allied work for Ragra and its adjoining mouzas PWSS in Sankrail Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000094/2024-2025 | 1278/JHD | 03/09/2024 | 28/10/2025 | ASIS KUMAR SARANGI | 76.24 | 0 | 0 | 0
Total | [13 empty] | 138.92 | 9.67 | 6.96