## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Interconnection between newly laid distribution pipeline with raising main and P.W.D road crossing work along with restoration for Manikpara PWSS under Jhargram Sub Division within Jhargram Division, P.H.E DTE. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000034/2022-2023 | 430/JSD | 05/08/2022 | 19/09/2022 | SOURABH KAR | 3.46 | 3.45 | 99.82 | 1
2 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Manikpara PWSS in Jhargram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000088/2021-2022 | 74/JSD | 25/06/2021 | 09/07/2021 | RADIANT | 3.62 | 3.6 | 99.46 | 1
3 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Manikpara PWSS in Jhargram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/000022/2022-2023 |  | 16/08/2022 | 16/08/2022 | RADIANT | 3.6 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Day to day operation & maintenance of Rising main & delivery main pipe line (CI/DI/ HDPE/UPVC/AC) with all related structure i.e. OHR etc. of Manikpara within Jhargram Sub Division under Jhargram Division, PHE Dte. from 01.10.2022 to 31.12.2022. | Assistant Engineer |  | ORD/000157/2022-2023 | 543/JSD | 23/09/2022 | 23/12/2022 | SOURABH KAR | 0.4 | 0 | 0 | 100
5 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Uploading, Development upgradation of all collected FHTC data and special features alongwith reorientation of JJM_ IMIS Dashboard (June-2023 to August-2023). | Assistant Engineer | Junior Engineer-III | ORD/000366/2023-2024 | 117A/JRWS | 31/05/2023 | 29/08/2023 | GOPAL JANA | 0.93 | 0.64 | 68.37 | 100
6 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 1706/JHD | 28/09/2023 | 28/09/2023 | Resource Division | 10.81 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | New service connection charges. |  |  | BILL/00261/2023-2024 | 18/JMD/PFMS/JUL | 31/07/2023 | 31/07/2023 | WBSEDCL | 3.02 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Laying Of Extention Distribution Pipe Line and Sinking Of T/W For Augmentation of Ground Water Based Manikpara Pwss to Accommodate FHTC In Jhargram Block Within Jhargram District Under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000317/2023-2024 | 1852/JHD | 31/10/2023 | 30/11/2023 | DIPAK KUMAR BAKLY | 35.03 | 29.52 | 84.25 | 100
9 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Providing additional FHTC under Manikpara W/S Scheme Jhargram Block under Jhargram Division, PHE Dte.( Part- A) | Assistant Engineer Headquarter | Junior Engineer, Jhargram Division | ORD/000574/2023-2024 | 444/JHD | 14/03/2024 | 29/03/2024 | KOUSIK MONDAL | 9.67 | 0 | 0 | 95
10 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Providing additional FHTC under Manikpara W/S Scheme Jhargram Block under Jhargram Division, PHE Dte. (Part-B) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000454/2023-2024 | 332/JHD | 28/02/2024 | 14/03/2024 | DIPAK KUMAR BAKLY | 9.96 | 0 | 0 | 95
11 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Augmentation of ground water based Manikpara Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work & Sinking of 250 mm x 150 mm x 165 m Tube Well and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Jhargram Dev. Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000029/2022-2023 | 252/JHD | 06/09/2022 | 05/03/2023 | DIPAK KUMAR BAKLY | 245.7 | 242.82 | 98.83 | 100
12 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I of Manikpara piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000051/2023-2024 | 1256/JMD | 26/05/2023 | 22/11/2023 | K.S.P. ENTERPRISE | 10.81 | 10.77 | 99.57 | 95
13 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Supply, delivery, installation, commissioning of pumping machinery and allied electro-mechanical works for Augmentation of t/w no. II of Manikpara water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | JE (M) | ORD/001045/2023-2024 | 2123/JMD | 22/02/2024 | 23/03/2024 | SUBHRA ENTERPRISE | 9.73 | 9.44 | 97.05 | 100
14 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10490 | Augmentation | Laying of rising main with interconnection with 2 nos tubewells and laying distribution pipeline from Manikpara Vivekananda more to propose O.H.R and by pass connection and Pump house for Augmentation of Manikpara PWSS in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000034/2023-2024 | 882/JHD | 08/06/2023 | 01/10/2024 | DIPAK KUMAR BAKLY | 33.98 | 26.58 | 78.22 | 95
Total | [13 empty] | 380.73 | 326.82 | 85.84