## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10491 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Kultikri PWSS in Sankrail Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-II | ORD/000123/2021-2022 | 60/JSD | 18/06/2021 | 02/07/2021 | ROY CHOWDHURY ASSOCIATES | 4.65 | 4.65 | 100 | 1
2 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10491 | Augmentation | Augmentation of Ground Water based Kultikri Water Supply Scheme by providing laying of Distribution pipe lie and FHTC work and Construction of RCC Over Head Reservoir of capacity 200 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sankrail Dev. Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000072/2022-2023 | 373/JHD | 18/10/2022 | 16/04/2023 | SIBSANKAR CHOWDHURY | 274.15 | 157.91 | 57.6 | 95
3 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10491 | Augmentation | Functional Household Tap Connection data uploading charges of different pwss under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for January-2023 and February-2023 under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000253/2022-2023 | 29A/JRWS | 28/12/2022 | 26/02/2023 | PROVAT KUMAR DE | 0.93 | 0.07 | 7.78 | 100
4 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10491 | Augmentation | Supply delivery of CIDF S/V for the work Augmentation Kultikri Water Supply Scheme under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000405/2023-2024 | 978/JSD | 17/11/2023 | 24/11/2023 | NRIPENDRA NATH SINGHA | 0.92 | 0.92 | 100 | 100
5 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10491 | Augmentation | Hatigeria Kultikri Rohini rogra road restoration work for laying pipelines along CH. 8.80 km to 12.50 Km done by PHE Jhargram under Jhargram Highway Division, in the District of Jhargram |  |  | BILL/00164/2023-2024 | BP-2023-24-108 | 28/06/2023 | 28/06/2023 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 18.27 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10491 | Augmentation | Balance road restoration charge for laying pipeling alogn hatigeria-Kultikri - Rohini Road under Kultikri W/S scheme under Jhrgram Highway Division, PHE Dte. |  |  | BILL/00497/2023-2024 | BP-2023-24-347 | 22/12/2023 | 22/12/2023 | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 18.27 | 0 | 0 | 0
Total | [13 empty] | 317.21 | 163.56 | 51.56