## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000213/2022-2023 | 340/JHD | 09/03/2023 | 28/07/2025 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 517.84 | 8.77 | 50
2 | JHARGRAM | Binpur-I | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 1509/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 6.71 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Chunpara at Binpur-I block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000614/2024-2025 | 6774/JMD | 27/08/2024 | 31/08/2024 | RSA ENTERPRISE | 3.49 | 0 | 0 | 100
4 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Bandhagora at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000600/2024-2025 | 6760/JMD | 27/08/2024 | 31/08/2024 | RSA ENTERPRISE | 1.56 | 0 | 0 | 0
5 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection charges |  |  | BILL/01214/2023-2024 | 50/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
6 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE NAMBANSHBER ( scheme code SM/11475) |  |  | BILL/00714/2024-2025 | 279/JMD | 31/07/2024 | 31/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
7 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection payment towards WBSEDCL for Shiyartola |  |  | BILL/00160/2024-2025 | 86/JMD | 07/05/2024 | 07/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
8 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | WBSEDCL New connection payment for Bara Brindabanpur |  |  | BILL/00509/2024-2025 | 232/JMD | 28/06/2024 | 28/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
9 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | Payment of New connection of WBSEDCL for Melkharia |  |  | BILL/00162/2024-2025 | 88/JMD | 07/05/2024 | 07/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
10 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection charge at Harulia |  |  | BILL/01213/2023-2024 | 50/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
11 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection payment towards WBSEDCL for Mohanpur |  |  | BILL/00508/2024-2025 | 231/JMD | 28/06/2024 | 28/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
12 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE ALAMDANGA ( scheme code SM/11475) |  |  | BILL/00712/2024-2025 | 277/JMD | 31/07/2024 | 31/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
13 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection at manpur under 179 Scheme.(Scheme code:- SM/11475) |  |  | BILL/01416/2024-2025 | 427/JMD | 28/11/2024 | 28/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
14 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection at Dhabani,Andharia GP |  |  | BILL/01209/2023-2024 | 50/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
15 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection charge at Bagghara,Dharampur GP |  |  | BILL/01210/2023-2024 | 50/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
16 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | WBSEDCL New connection payment for Benakharanga |  |  | BILL/00158/2024-2025 | 85/JMD | 07/05/2024 | 07/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
17 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | Payment of New connection of WBSEDCL for Jualbhanga |  |  | BILL/00161/2024-2025 | 87/JMD | 07/05/2024 | 07/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
18 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection at Baita under 179 Scheme.(Scheme code:- SM/11475) |  |  | BILL/01417/2024-2025 | 428/JMD | 28/11/2024 | 28/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
19 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection charge at Padiha |  |  | BILL/01212/2023-2024 | 50/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
20 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE OF MOHANPUR (scheme code SM/11475 ) |  |  | BILL/00713/2024-2025 | 278/JMD | 31/07/2024 | 31/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
21 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | New service connection at Chantukasda,Ramgarh GP |  |  | BILL/01211/2023-2024 | 50/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
22 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | Supply, delivery and installation of different fast moving spare parts for KLR/DR/DTH-500 departmental rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000990/2024-2025 | 15/W/MMSD(D) | 13/01/2025 | 23/01/2025 | B. P. TRADING CORPORATION | 0.86 | 0 | 0 | 100
23 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 | New | Supply & delivery of different size hydraulic hose for departmental rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000989/2024-2025 | 14/W/MMSD(D) | 13/01/2025 | 23/01/2025 | B. P. TRADING CORPORATION | 0.96 | 0 | 0 | 100
Total | [13 empty] | 5923.27 | 517.84 | 8.74