## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 1511/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 8.21 | 0 | 0 | 0
2 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Matihana at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000602/2024-2025 | 6762/JMD | 27/08/2024 | 31/08/2024 | RSA ENTERPRISE | 1.56 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Dahi at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000604/2024-2025 | 6764/JMD | 27/08/2024 | 31/08/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
4 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Ranjia at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000605/2024-2025 | 6765/JMD | 27/08/2024 | 31/08/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Chaqua at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000606/2024-2025 | 6766/JMD | 27/08/2024 | 31/08/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
6 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Madhabpur at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000615/2024-2025 | 6775/JMD | 27/08/2024 | 01/01/2025 | RSA ENTERPRISE | 3.49 | 0 | 0 | 100
7 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Kachmabila at Gopiballavpur-I block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000603/2024-2025 | 6763/JMD | 27/08/2024 | 31/08/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
8 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Jamdahari at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000609/2024-2025 | 6769/JMD | 27/08/2024 | 31/08/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
9 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Mahupal at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000607/2024-2025 | 6767/JMD | 27/08/2024 | 31/08/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
10 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Kamarbandi at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000596/2024-2025 | 6756/JMD | 27/08/2024 | 31/08/2024 | RSA ENTERPRISE | 1.56 | 0 | 0 | 0
11 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | New Service connection charges. |  |  | BILL/01149/2023-2024 | 32/JMD | 18/01/2024 | 18/01/2024 | WBSEDCL | 0.42 | 0 | 0 | 0
12 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. (scheme code:- SM/11477) |  |  | BILL/01366/2024-2025 | 423/JMD | 27/11/2024 | 27/11/2024 | SURAJ SERVICE STATION | 0.12 | 0 | 0 | 0
13 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | New service connection charges for Phulakendu mini pwss |  |  | BILL/00015/2024-2025 | 15/JMD | 18/04/2024 | 18/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
14 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | New Service connection charges. |  |  | BILL/01138/2023-2024 | 19/JMD | 11/01/2024 | 11/01/2024 | WBSEDCL | 0.42 | 0 | 0 | 0
15 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | New Service connection charges for Muchinala mini pwss |  |  | BILL/00099/2024-2025 | 72/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
16 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000213/2022-2023 | 340/JHD | 09/03/2023 | 28/07/2025 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 301.27 | 5.1 | 50
17 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Panchberia at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | DIC(D)_MMSD(D),Driller-In-Charge | JE (M) | ORD/000610/2024-2025 | 6770/JMD | 27/08/2024 | 01/01/2025 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 100
18 | JHARGRAM | Binpur-II,Gopiballavpur-I,Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Banbhum at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000611/2024-2025 | 6771/JMD | 27/08/2024 | 01/01/2025 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 100
Total | [13 empty] | 5949.7 | 301.27 | 5.06