## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 1511/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 7.87 | 0 | 0 | 0
2 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Balidiha at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000608/2024-2025 | 6768/JMD | 27/08/2024 | 30/09/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 100
3 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | new service connection for Kaliam water supply scheme |  |  | BILL/00001/2024-2025 | 01/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
4 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | Fuel & lubricant charges which is used at Rig unit HALCO for boring purpose at the site of Balidiha under 179 scheme(SM/11478) under Jamboni block |  |  | BILL/01367/2024-2025 | 424/JMD | 27/11/2024 | 27/11/2024 | SURAJ SERVICE STATION | 0.53 | 0 | 0 | 0
5 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | New Service Connection Charges for Chirkundihi PWSS |  |  | BILL/00164/2024-2025 | 83/JMD | 07/05/2024 | 07/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
6 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | New Service Connection Charges for Bhalukhuliya PWSS |  |  | BILL/00165/2024-2025 | 84/JMD | 07/05/2024 | 07/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
7 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | New Service Connection Charges for Kapashi PWSS |  |  | BILL/00163/2024-2025 | 82/JMD | 07/05/2024 | 07/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
8 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | new service connection charges at Juasole,Parsuli water supply scheme |  |  | BILL/00002/2024-2025 | 02/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
9 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | New service connection |  |  | BILL/01294/2023-2024 | 65/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 0.84 | 0 | 0 | 0
10 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000213/2022-2023 | 340/JHD | 09/03/2023 | 28/07/2025 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 158.7 | 2.69 | 50
11 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 | New | Supply , Delivery of Hydraulic pump for rotation motor of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001031/2024-2025 | 16/W/MMSD(D) | 13/01/2025 | 23/01/2025 | CHAKRABORTY MINING & ENGINEERING | 0.97 | 0 | 0 | 100
Total | [13 empty] | 5920.81 | 158.7 | 2.68