## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 1510/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 6.73 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Kismat Balibhasa at Jhargram block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000612/2024-2025 | 6772/JMD | 27/08/2024 | 31/08/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 0
3 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Parihati at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000531/2024-2025 | 6717/JMD | 23/08/2024 | 27/08/2024 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0 | 100
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | new service connection charges at Chhota Ektal water supply scheme |  |  | BILL/00098/2024-2025 | 71/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | new service connection charges at Kasitoria water supply scheme |  |  | BILL/00264/2024-2025 | 119/JMD | 13/05/2024 | 13/05/2024 | WBSEDCL | 2.44 | 0 | 0 | 0
6 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | new service connection for Ashanbani water supply scheme |  |  | BILL/00010/2024-2025 | 4/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
7 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | New Service connection charges |  |  | BILL/01131/2023-2024 | 12/JMD | 09/01/2024 | 09/01/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | new service connection charges at Kumari water supply scheme |  |  | BILL/00008/2024-2025 | 2/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | NEW SERVICE CONNECTION CHARGES AT KISMAT BAGJHAPA WATER SUPPLY SCHEME |  |  | BILL/00263/2024-2025 | 118/JMD | 13/05/2024 | 13/05/2024 | WBSEDCL | 2.98 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | Fuel & lubricant charges which is used at Rig unit HALCO for boring purpose at the site of Parihati under 179 scheme(SM/11479) under Jamboni block |  |  | BILL/01365/2024-2025 | 422/JMD | 27/11/2024 | 27/11/2024 | SURAJ SERVICE STATION | 0.54 | 0 | 0 | 0
11 | JHARGRAM | Jhargram | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000213/2022-2023 | 340/JHD | 09/03/2023 | 28/07/2025 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 231.92 | 3.93 | 50
Total | [13 empty] | 5929.65 | 231.92 | 3.91