## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram,Nayagram | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000213/2022-2023 | 340/JHD | 09/03/2023 | 28/07/2025 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 623.8 | 10.56 | 50
2 | JHARGRAM | Jhargram,Nayagram | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 1514/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 7.5 | 0 | 0 | 0
3 | JHARGRAM | Jhargram,Nayagram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | New Service connection charges. |  |  | BILL/01216/2023-2024 | 47/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 2.1 | 0 | 0 | 0
4 | JHARGRAM | Jhargram,Nayagram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | New service connection charges for Bhaliadiha. |  |  | BILL/00004/2024-2025 | 8/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
5 | JHARGRAM | Jhargram,Nayagram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | New service connection charges for Jangal Khas |  |  | BILL/00005/2024-2025 | 9/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
6 | JHARGRAM | Jhargram,Nayagram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | New Service connection charges |  |  | BILL/01132/2023-2024 | 13/JMD | 09/01/2024 | 09/01/2024 | WBSEDCL | 1.47 | 0 | 0 | 0
7 | JHARGRAM | Jhargram,Nayagram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | New service connection charges for Darkhuli |  |  | BILL/00003/2024-2025 | 7/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
8 | JHARGRAM | Jhargram,Nayagram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | new service connection charges at Krishnanagar water supply scheme |  |  | BILL/00184/2024-2025 | 104/JMD | 08/05/2024 | 08/05/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
9 | JHARGRAM | Jhargram,Nayagram | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 | New | New service connection charges for Salgeria PWSS |  |  | BILL/00705/2024-2025 | 269/JMD | 26/07/2024 | 26/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
Total | [13 empty] | 5918.25 | 623.8 | 10.54