## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | SM/11481 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 179 (one hundred and seventy-nine) nos. villages under different Blocks having less than 100 household under Jhargram District in connection with Jal Swapna. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000213/2022-2023 | 340/JHD | 09/03/2023 | 28/07/2025 | JHARGRAM SPV PRIVATE LIMITED | 5906.13 | 0 | 0 | 50
2 | JHARGRAM | Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | SM/11481 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 1513/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 4.05 | 0 | 0 | 0
3 | JHARGRAM | Nayagram,Sankrail | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | SM/11481 | New | NEW SERVICE CONNECTION CHARGES FOR CHOTOKANYADIHA PWSS |  |  | BILL/01385/2023-2024 | 48/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
4 | JHARGRAM | Nayagram,Sankrail | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | SM/11481 | New | New Service connection charges. |  |  | BILL/01215/2023-2024 | 46/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 1.26 | 0 | 0 | 0
5 | JHARGRAM | Nayagram,Sankrail | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | SM/11481 | New | New service connection charges for Ichhapura |  |  | BILL/00006/2024-2025 | 03/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
6 | JHARGRAM | Nayagram,Sankrail | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | SM/11481 | New | New service connection charges for Rangamatia |  |  | BILL/00009/2024-2025 | 10/JMD | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
7 | JHARGRAM | Nayagram,Sankrail | Jhargram Mechanical Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | SM/11481 | New | NEW SERVICE CONNECTION CHARGES FOR SHIYALIA PWSS |  |  | BILL/01384/2023-2024 | 47/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
Total | [13 empty] | 5912.28 | 0 | 0