## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | SM/12324 | New | New service connection |  |  | BILL/00338/2023-2024 | 17/AUG | 24/08/2023 | 24/08/2023 | WBSEDCL | 3.06 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | SM/12324 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Barsol and its adjoining mouzas Pipe Water Supply Scheme within Gopialavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000555/2023-2024 | 191/GPSD | 11/03/2024 | 10/04/2024 | ENVOTECH INFRA SOLUTION | 4.24 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | SM/12324 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 419/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 15.79 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | SM/12324 | New | Quotation for new service connection at Barsole T/W -I water supply scheme. |  |  | BILL/00507/2024-2025 | 230/JMD | 28/06/2024 | 28/06/2024 | WBSEDCL | 5.37 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | SM/12324 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 343.29 | 2.79 | 25
6 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | SM/12324 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bhila, Gohalbura and Barasol and its adjoining Mouzas , Block Gopiballavpur-I, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-III | ORD/000299/2024-2025 | 313/JHD | 12/02/2025 | 13/04/2025 | ANUSKA ENTERPRISE | 43.87 | 0 | 0 | 0
Total | [13 empty] | 12357.09 | 343.29 | 2.78