## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Mechanical Division | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. | SM/12326 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Simli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000070/2023-2024 | 1241/JMD | 26/05/2023 | 22/11/2023 | T.N. BANERJEE | 20.82 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Central Drilling | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. | SM/12326 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Driller In Charge | Junior Engineer | ORD/000001/2024-2025 | 91/CDD | 25/04/2024 | 25/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 9.68 | 6.24 | 10
3 | JHARGRAM | Jhargram | Jhargram Division | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. | SM/12326 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
4 | JHARGRAM | Jhargram | Jhargram Division | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. | SM/12326 | New | Hire charges of additional Bharat Stage-II / III Diesel Motor Cabs (Luxury Taxi) / Maruti Omni (Standard - Non - Air Conditioned) having Contract Carriage Permit from the Regional Transport Authority for the use of Assistant Engineer(H.Q) under Office of the Executive Engineer, Jhargram Division, PHE Dte. For the period of 12 (Twelve) Months. (01/03/2025 to 28/02/2026) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000313/2024-2025 | 365/JHD | 20/02/2025 | 20/02/2026 | SUNIL DULE | 1.73 | 0 | 0 | 0
Total | [13 empty] | 12462.33 | 9.68 | 0.08