## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Mechanical Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | SM/12327 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uransoal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000042/2023-2024 | 1245/JMD | 26/05/2023 | 30/04/2025 | MANAS KUMAR SAHA | 21.75 | 0 | 0 | 40
2 | JHARGRAM | Jhargram | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | SM/12327 | New | Laying distribution pipe line under JJM with allied work for URNASAOL AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000070/2023-2024 | 1107/JHD | 18/07/2023 | 28/07/2025 | SUNIL DULE | 143.61 | 79.44 | 55.31 | 91
3 | JHARGRAM | Jhargram | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | SM/12327 | New | Sinking of Tube Well, Pump House, 100 cum GLR, Rising main pipe line, Interconnection pipe line, Installation of display Board, Accommodate FHTC (1451 nos) under JJM with allied work for URNASAOL AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_31 of 2022-23, SL No.-3) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000333/2023-2024 | 1836/JHD | 27/10/2023 | 27/12/2025 | SUNIL DULE | 160.92 | 32.59 | 20.25 | 60
4 | JHARGRAM | Jhargram | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | SM/12327 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 200 cum and staging height 20 mtr. as per approved drawing with allied works of URANSOL & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for JHARGRAM Block, District: - Jhargram. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000382/2023-2024 | 2053/JHD | 07/12/2023 | 04/07/2024 | SATYABRATA BHAUMIK | 71.95 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | SM/12327 | New | Construction of boundary wall and Allied works At Chakua, Uransol, Patharnala 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000096/2024-2025 | 1281/JHD | 03/09/2024 | 03/10/2024 | SUNIL DULE | 37.46 | 0 | 0 | 0
6 | JHARGRAM | Jhargram | Jhargram Mechanical Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | SM/12327 | New | new service connection charge for Uransole water supply scheme |  |  | BILL/00019/2024-2025 | 18/JMD | 18/04/2024 | 18/04/2024 | WBSEDCL | 7.1 | 0 | 0 | 0
7 | JHARGRAM | Jhargram | Jhargram Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | SM/12327 | New | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of Propose O.H.R. for Chakkua, Uransol PWSS in Jhargram Block within Jhargram District under Jhargram Division, P.H.E.Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000359/2024-2025 | 366/JHD | 20/03/2025 | 19/04/2025 | M/S. M.D. ENGINEERING & SURVEYS | 1.59 | 0 | 0 | 0
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | SM/12327 | New | NEW SERVICE CONNECTION CHARGES AT URANSOLE-II PWSS |  |  | BILL/01646/2024-2025 | 504/JMD | 10/02/2025 | 10/02/2025 | WBSEDCL | 5.12 | 0 | 0 | 0
Total | [13 empty] | 449.5 | 112.03 | 24.92