## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12328 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Dudkundi GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000115/2024-2025 | 1841/JHD | 20/09/2024 | 30/09/2024 | MANOJ KUMAR MAHATA | 0.58 | 0.58 | 100 | 100
2 | JHARGRAM | Jhargram | Jhargram Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12328 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Lodhasuli GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000116/2024-2025 | 1842/JHD | 20/09/2024 | 30/09/2024 | GOPAL JANA | 0.92 | 0.92 | 100 | 100
3 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12328 | New | new service connection charges at Burimole-2 water supply scheme |  |  | BILL/00100/2024-2025 | 73/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.72 | 0 | 0 | 0
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12328 | New | new service connection charges at Burimol-1 water supply scheme |  |  | BILL/00101/2024-2025 | 74/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 5.38 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Central Drilling | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12328 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 35.27 | 0.17 | 11
6 | JHARGRAM | Jhargram | Jhargram Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12328 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 68.88 | 0.56 | 25
7 | JHARGRAM | Jhargram | Jhargram Division | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12328 | New | Construction of boundary wall and Allied works At Burimol, Rajband, Bhaudi , Metial 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000023/2024-2025 | 1077/JHD | 25/07/2024 | 21/02/2025 | M/S MITRA BROTHERS | 48.9 | 0 | 0 | 40
Total | [13 empty] | 33684.03 | 105.65 | 0.31