## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Sankrail | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1497/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 37.5 | 0 | 0 | 0
2 | JHARGRAM | Sankrail | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | New Service connection |  |  | BILL/00703/2023-2024 | 27/JMD | 29/11/2023 | 29/11/2023 | WBSEDCL | 0.12 | 0 | 0 | 0
3 | JHARGRAM | Sankrail | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | New service connection charges |  |  | BILL/00253/2023-2024 | 16/JMD/PFMS/APR | 27/07/2023 | 27/07/2023 | WBSEDCL | 6.48 | 0 | 0 | 0
4 | JHARGRAM | Sankrail | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | Revused Quotation for New service connection |  |  | BILL/00392/2023-2024 | 30/AUG | 29/08/2023 | 29/08/2023 | WBSEDCL | 0 | 0 | 0 | 0
5 | JHARGRAM | Sankrail | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | New Service connection |  |  | BILL/00672/2023-2024 | 19/JMD | 20/11/2023 | 20/11/2023 | WBSEDCL | 5.55 | 0 | 0 | 0
6 | JHARGRAM | Sankrail | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gobindapur & adjoining moujas piped water supply scheme, Block- Sankrail in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000200/2023-2024 | 2261/JMD | 09/08/2023 | 05/02/2024 | M/S. EMMESS | 21.77 | 9.24 | 42.46 | 90
7 | JHARGRAM | Sankrail | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of GOBINDAPUR and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000478/2023-2024 | 167/GPSD | 05/03/2024 | 04/04/2024 | SAURABH KAR | 4.26 | 4.02 | 94.24 | 100
8 | JHARGRAM | Sankrail | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system ,Pump House ,& Providing Functional Household Tap Connection (7650 Nos), etc. For BAKRA, GOBINDAPUR, HARIPURBIRUA, KARKATASOL, Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000226/2022-2023 | 443/JHD | 23/03/2023 | 01/10/2025 | GOBINDA MAITY | 2154.34 | 257.71 | 11.96 | 70
9 | JHARGRAM | Sankrail | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Gobindapur and its adjoining Mouzas, Block Sankrail, District Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000011/2024-2025 | 915/JHD | 08/07/2024 | 07/08/2024 | GANGULY ENTERPRISE | 8.25 | 2.17 | 26.33 | 90
10 | JHARGRAM | Sankrail | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Gobindapur and its adjoining mouzas Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000350/2024-2025 | 131/GPSD | 18/03/2025 | 08/04/2025 | GOBINDA MAITY | 1.85 | 0 | 0 | 100
Total | [13 empty] | 2240.13 | 273.14 | 12.19