## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | SM/12330 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of KANKRIDAHI & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-I Block, District: - Jhargram. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000384/2023-2024 | 2058/JHD | 07/12/2023 | 04/07/2024 | ASIS KUMAR SARANGI | 73.5 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | SM/12330 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 1582/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 83.7 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | SM/12330 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Kankridahi and its adjoining mouzas Pipe Water Supply Scheme within Gopaballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000563/2023-2024 | 199/GPSD | 11/03/2024 | 10/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 4.3 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | SM/12330 | New | New Service Connection Charges for Kakridahi t/w-II pwss |  |  | BILL/01194/2023-2024 | 35/JMD | 01/02/2024 | 01/02/2024 | WBSEDCL | 2.67 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | SM/12330 | New | New Service Connection Charges for Kakridahi tw-I pwss |  |  | BILL/01195/2023-2024 | 36/JMD | 01/02/2024 | 01/02/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
6 | JHARGRAM | Gopiballavpur-I | Jhargram Division | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | SM/12330 | New | Sinking of Tube Well , Pump House , 100 cum GLR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Operation and Maintenance and Accommodate FHTC ( 1288 nos) under JJM with allied work for KANKRIDAHI AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000083/2023-2024 | 1129/JHD | 20/07/2023 | 09/07/2025 | ASIS KUMAR SARANGI | 308.99 | 203.53 | 65.87 | 95
Total | [13 empty] | 476.36 | 203.53 | 42.73