## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1596/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 57.15 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Rautarapur & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000046/2023-2024 | 1249/JMD | 26/05/2023 | 22/11/2023 | MAA BHABOTARINE ENTERPRISE | 21.88 | 16.48 | 75.32 | 50
3 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000044/2023-2024 | 873/JHD | 08/06/2023 | 06/09/2023 | TAPAN KUMAR UPADHYAY | 25.78 | 23.99 | 93.08 | 80
4 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000156/2023-2024 | 1374/JHD | 16/08/2023 | 14/11/2023 | LAKSHMI IRON | 33.9 | 31.79 | 93.77 | 95
5 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_27 of 2022-23 , SL No.-9 ) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000206/2023-2024 | 1580/JHD | 08/09/2023 | 07/12/2023 | GANGULY ENTERPRISE | 14.67 | 12.44 | 84.8 | 95
6 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Accommodate FHTC ( 1531 nos) under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000202/2023-2024 | 1499/JHD | 05/09/2023 | 30/08/2024 | MONDAL ENTERPRISE | 64.5 | 0 | 0 | 70
7 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3 rd Call (Ref: 1st Call eNIT_27 of 2022-23, SL No.-3 and 2nd Call eNIT_08 of 2023-24, SL No.-12) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000351/2023-2024 | 1950/JHD | 22/11/2023 | 20/02/2024 | MASUM CONSTRUCTION | 17.09 | 14.42 | 84.33 | 100
8 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Rautarapur and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000206/2024-2025 | 2294/JHD | 04/12/2024 | 03/01/2025 | BIKASH MANDAL | 7.92 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | new service connection charges at Rautarapur, T/W-1 water supply scheme |  |  | BILL/00104/2024-2025 | 77/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 9.06 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | new service connection charges at Rautrapur t/w-2 water supply scheme |  |  | BILL/00103/2024-2025 | 76/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 6.82 | 0 | 0 | 0
11 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_27 of 2022-23 , SL No.-4 ) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000400/2023-2024 | 3090/JHD | 28/12/2023 | 27/03/2024 | TARUN MAHATA | 23.06 | 0 | 0 | 95
12 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Rautarapur and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000264/2024-2025 | 75/JHD | 10/01/2025 | 09/02/2025 | ENVOTECH INFRA SOLUTION | 8.39 | 0 | 0 | 0
13 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Boundary wall and allied works at 2nd. Tube well site of Rautarapur and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 50 mtr, column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000126/2024-2025 | 1318/JHD | 23/09/2024 | 23/10/2024 | BISWANATH PANIGRAHI | 3.67 | 0 | 0 | 100
14 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Additional Laying of Distribution pipe line for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000319/2024-2025 | 372/JHD | 20/02/2025 | 06/04/2025 | MASUM CONSTRUCTION | 5.78 | 0 | 0 | 0
15 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Trial run for RAUTARAPUR AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000002/2025-2026 | 731/JHD | 02/04/2025 | 02/07/2025 | ENVOTECH INFRA SOLUTION | 1.29 | 0 | 0 | 0
16 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000066/2023-2024 | 1093/JHD | 14/07/2023 | 12/10/2023 | ASSOCIATED ENGINEERS & TRADERS | 23.96 | 20.82 | 86.88 | 90
17 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_27 of 2022-23 , SL No.-8 ) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000133/2023-2024 | 1342/JHD | 10/08/2023 | 08/11/2023 | SANDIP GURIA | 14.78 | 13.3 | 89.96 | 95
18 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Construction of Laying distribution pipe line under JJM with allied work for RAUTARAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000210/2023-2024 | 1615/JHD | 08/09/2023 | 07/12/2023 | A.K. SIKDAR | 31.62 | 28.51 | 90.16 | 100
19 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | Laying of extention distribution pipe line for rautarapur and adjoining moujas pwss in jhargram block within jhargram district under jhargram division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division,Junior Engineer-II | ORD/000086/2024-2025 | 1243/JHD | 30/08/2024 | 14/10/2024 | MMS CONSTRUCTIONS PVT.LTD. | 15.05 | 0 | 0 | 100
20 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | GI CASING AT CULVERT CROSSING OVER MINI CANAL AT RAUTARAPUR AND ADJOINING MOUZAS PWSS WITHIN JHARGRAM BLOCK UNDER JHARGRAM DIVISION, PHE DTE. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000382/2024-2025 | 21/JHD | 03/01/2025 | 02/02/2025 | TAPAN KUMAR UPADHYAY | 0.66 | 0 | 0 | 100
21 | JHARGRAM | Jhargram | Jhargram Division | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 | New | GI CASING AT UNDERGROUND ROAD CROSSING AT RAUTARAPUR AND ADJOINING MOUZAS PWSS WITHIN JHARGRAM BLOCK UNDER JHARGRAM DIVISION, PHE DTE. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000381/2024-2025 | 20/JHD | 03/01/2025 | 02/02/2025 | TAPAN KUMAR UPADHYAY | 0.77 | 0 | 0 | 100
Total | [13 empty] | 387.81 | 161.74 | 41.71