## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Sankrail | Jhargram Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12334 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 956/JHD | 22/06/2023 | 22/06/2023 | Resource Division | 33.32 | 0 | 0 | 0
2 | JHARGRAM | Sankrail | Jhargram Mechanical Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12334 | New | New Service connection |  |  | BILL/00706/2023-2024 | 29/JMD | 29/11/2023 | 29/11/2023 | WBSEDCL | 0.11 | 0 | 0 | 0
3 | JHARGRAM | Sankrail | Jhargram Mechanical Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12334 | New | New Service connection |  |  | BILL/00674/2023-2024 | 21/JMD | 20/11/2023 | 20/11/2023 | WBSEDCL | 5.65 | 0 | 0 | 0
4 | JHARGRAM | Sankrail | Jhargram Mechanical Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12334 | New | New Service Connection Charges for Satkuli P.H - II PWSS |  |  | BILL/00577/2024-2025 | 256/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 6.79 | 0 | 0 | 0
5 | JHARGRAM | Sankrail | Jhargram Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12334 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House , & Providing Functional Household Tap Connection (6745 Nos), etc. For RAGRA, SATKULI CHARAR, NOAGAON, RAMPURA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000008/2023-2024 | 607/JHD | 04/05/2023 | 01/10/2025 | GOBINDA MAITY | 1886.45 | 430.77 | 22.83 | 20
6 | JHARGRAM | Sankrail | Jhargram Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12334 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chhatri, Dhanghori GP at Sankrail Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000236/2024-2025 | 649/GPSD | 19/11/2024 | 29/11/2024 | MANOJ KUMAR MAHATA | 0.84 | 0.74 | 88.93 | 100
7 | JHARGRAM | Sankrail | Jhargram Division | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12334 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Khudimorai GP at Sankrail Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000237/2024-2025 | 650/GPSD | 19/11/2024 | 29/11/2024 | PRINT PREVIEW | 0.84 | 0.66 | 79.05 | 100
Total | [13 empty] | 1933.99 | 432.17 | 22.35