## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Laying distribution pipe line under JJM with allied work for AMLACHATI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000015/2023-2024 | 650/JHD | 11/05/2023 | 09/08/2023 | R. CONSTRUCTION | 39.7 | 36.75 | 92.57 | 100
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Amlachati & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000037/2023-2024 | 1235/JMD | 26/05/2023 | 22/11/2023 | S.S. GHORAI | 20.79 | 17.03 | 81.9 | 70
3 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Boundary wall, Installation of display Board, soil investigation under JJM with allied work for AMLACHATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (2nd Call Ref eNIT_18 of 2022-23 , SL No.-1 ) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000127/2023-2024 | 1334/JHD | 10/08/2023 | 07/03/2024 | SUBHANKAR BANERJEE | 199.53 | 167.48 | 83.94 | 95
4 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Sinking of Tube Well , Interconnection pipe line, Laying distribution pipe line, under JJM with allied work for AMLACHATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000151/2023-2024 | 1324/JHD | 10/08/2023 | 08/11/2023 | BISHNU PADA NANDI | 23.33 | 22.05 | 94.49 | 100
5 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Accommodate FHTC ( 1414 nos) under JJM with allied work for AMLACHATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000183/2023-2024 | 1415/JHD | 22/08/2023 | 14/05/2025 | M/S. D.K.H.CONSTRUCTION | 59.36 | 0 | 0 | 30
6 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Construction of Laying distribution pipe line under JJM with allied work for AMLACHATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000150/2023-2024 | 1323/JHD | 10/08/2023 | 08/11/2023 | RAMENDRA NATH KAR | 50.31 | 48.62 | 96.63 | 95
7 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 1593/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 30.87 | 0 | 0 | 0
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | New Service connection |  |  | BILL/00773/2023-2024 | 13/JMD | 07/12/2023 | 07/12/2023 | WBSEDCL | 2.82 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | New Service connection |  |  | BILL/00774/2023-2024 | 14/JMD | 07/12/2023 | 07/12/2023 | WBSEDCL | 6.12 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Amlachati and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000211/2024-2025 | 2293/JHD | 04/12/2024 | 03/01/2025 | TAPAS KUMAR HAZRA | 7.92 | 0 | 0 | 0
11 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Extention distribution pipe line for amlachati and adjoining moujas pwss in jhargram block within jhargram district under jhargram division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000084/2024-2025 | 1214/JHD | 27/08/2024 | 11/10/2024 | SAURABH KAR | 7.97 | 0 | 0 | 90
12 | JHARGRAM | Jhargram | Jhargram Division | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 | New | Construction of boundary wall and Allied works At Amlachati 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000183/2024-2025 | 2195/JHD | 22/11/2024 | 22/12/2024 | RAMENDRA NATH KAR | 12.07 | 0 | 0 | 100
Total | [13 empty] | 460.79 | 291.93 | 63.35