## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I,Gopiballavpur-II | Jhargram Division | GOHALMARA AND ADJOINING MOUJAS PWSS | SM/12340 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1550/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 33.8 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I,Gopiballavpur-II | Jhargram Mechanical Division | GOHALMARA AND ADJOINING MOUJAS PWSS | SM/12340 | New | Quotation for new service connection at Gohalmara water supply scheme T/W - I |  |  | BILL/00022/2024-2025 | 21/JMD | 19/04/2024 | 19/04/2024 | WBSEDCL | 3.41 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I,Gopiballavpur-II | Jhargram Mechanical Division | GOHALMARA AND ADJOINING MOUJAS PWSS | SM/12340 | New | Quotation for new service connection at Gohalmara water supply scheme T/W-II |  |  | BILL/00023/2024-2025 | 22/JMD | 19/04/2024 | 19/04/2024 | WBSEDCL | 4 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I,Gopiballavpur-II | Jhargram Division | GOHALMARA AND ADJOINING MOUJAS PWSS | SM/12340 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 256.28 | 2.09 | 25
5 | JHARGRAM | Binpur-I,Gopiballavpur-II | Jhargram Division | GOHALMARA AND ADJOINING MOUJAS PWSS | SM/12340 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in fferent Pipe Water Supply Scheme (7 nos PWSS of 130 PWSS) within Gopiballavpur-II Block in the District of Jhargram under Jhargram Division. PHE Dte. Location- i) Chingra PWSS, ii) Gohalmara PWSS iii) Kendana PWSS iv) Kulina PWSS v) Sonakinia PWSS Vi) Tentilia PWSS vii) Chorchita PWSS | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000030/2025-2026 | 368/JSD | 29/04/2025 | 26/09/2025 | TECHVISION | 3.72 | 0 | 0 | 10
6 | JHARGRAM | Binpur-I,Gopiballavpur-II | Jhargram Division | GOHALMARA AND ADJOINING MOUJAS PWSS | SM/12340 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Ghohalmara and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division,Junior Engineer-III | ORD/000068/2024-2025 | 780/JSD | 09/08/2024 | 08/09/2024 | MAA RAJBALLABHI ENTERPRISE | 4.69 | 0 | 0 | 100
Total | [13 empty] | 12334.38 | 256.28 | 2.08