## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | JUNSOLA AND ADJOINING MOUJAS PWSS | SM/12342 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Junsola & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000030/2023-2024 | 1227/JMD | 26/05/2023 | 22/11/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD | 20.73 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-II | Jhargram Division | JUNSOLA AND ADJOINING MOUJAS PWSS | SM/12342 | New | Sinking of Tube Well , Pump House, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board & Accommodate FHTC(6721 nos) including 02(Two) Years Operation & Maintenance under JJM with allied work for DHADANGIRI, GOBINDAPUR, JUNSOLA, PETBINDHI & MAHAPAL PWSS in Gopiballavpur-II Block including supply of all labour & materials within Gopiballavpur Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000152/2023-2024 | 1373/JHD | 16/08/2023 | 23/11/2024 | M/S. EL-CON | 1574.44 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-II | Jhargram Division | JUNSOLA AND ADJOINING MOUJAS PWSS | SM/12342 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of JUNSOLA & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-II Block, District: - Jhargram. | Assistant Engineer | Junior Engineer-III | ORD/000378/2023-2024 | 2051/JHD | 07/12/2023 | 04/07/2024 | ABJ ENGINEERING | 71.51 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-II | Jhargram Division | JUNSOLA AND ADJOINING MOUJAS PWSS | SM/12342 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1560/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 22.19 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-II | Central Drilling | JUNSOLA AND ADJOINING MOUJAS PWSS | SM/12342 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000202/2023-2024 | 2104/CDD | 09/02/2024 | 09/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 110.72 | 0 | 0 | 10
Total | [13 empty] | 1799.59 | 0 | 0