## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1553/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 181.8 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Construction of Boundary wall allied works at 3rd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Simladanga and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000059/2024-2025 | 778/JSD | 09/08/2024 | 08/09/2024 | ARUP KUMAR MAITI | 4.39 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Simladanga and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000079/2024-2025 | 776/JSD | 09/08/2024 | 08/09/2024 | CONSTRUCTURE | 4.81 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Quotation for new service connection at Simladanga tw-III water supply scheme. |  |  | BILL/00389/2024-2025 | 185/JMD | 11/06/2024 | 11/06/2024 | WBSEDCL | 5.94 | 0 | 0 | 0
5 | JHARGRAM | Binpur-I | Central Drilling | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | JHARGRAM | Binpur-I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Belatikri GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division,Junior Engineer-II | ORD/000413/2024-2025 | 965/JSD | 30/09/2024 | 10/10/2024 | GOPAL JANA | 0.92 | 0 | 0 | 0
7 | JHARGRAM | Binpur-I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Dharampur GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division,Junior Engineer-II | ORD/000414/2024-2025 | 966/JSD | 30/09/2024 | 10/10/2024 | PRINT PREVIEW | 0.84 | 0 | 0 | 0
Total | [13 empty] | 21538.47 | 0 | 0