## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1553/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 181.8 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Construction of Boundary wall allied works at 3rd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Simladanga and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000059/2024-2025 | 778/JSD | 09/08/2024 | 08/09/2024 | ARUP KUMAR MAITI | 4.39 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Simladanga and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000079/2024-2025 | 776/JSD | 09/08/2024 | 08/09/2024 | CONSTRUCTURE | 4.81 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Quotation for new service connection at Simladanga tw-III water supply scheme. |  |  | BILL/00389/2024-2025 | 185/JMD | 11/06/2024 | 11/06/2024 | WBSEDCL | 5.94 | 0 | 0 | 0
Total | [13 empty] | 196.95 | 0 | 0