## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Sankrail | Jhargram Division | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 1507/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 29.73 | 0 | 0 | 0
2 | JHARGRAM | Sankrail | Jhargram Mechanical Division | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 | New | New Service connection |  |  | BILL/00673/2023-2024 | 20/JMD | 20/11/2023 | 20/11/2023 | WBSEDCL | 3.13 | 0 | 0 | 0
3 | JHARGRAM | Sankrail | Jhargram Mechanical Division | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 | New | New service connection charges |  |  | BILL/00248/2023-2024 | 11/JMD/PFMS/JUL | 27/07/2023 | 27/07/2023 | WBSEDCL | 2.31 | 0 | 0 | 0
4 | JHARGRAM | Sankrail | Jhargram Mechanical Division | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 | New | New Service connection |  |  | BILL/00704/2023-2024 | 28/JMD | 29/11/2023 | 29/11/2023 | WBSEDCL | 0.05 | 0 | 0 | 0
5 | JHARGRAM | Sankrail | Jhargram Division | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Jaqua-I and its adjoining Mouzas, Block Sankrail, District Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000047/2024-2025 | 1135/JHD | 06/08/2024 | 05/09/2024 | S.R. ENTERPRISE | 8.15 | 0 | 0 | 80
6 | JHARGRAM | Sankrail | Jhargram Division | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of JAQUA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000497/2023-2024 | 170/GPSD | 05/03/2024 | 04/04/2024 | ASHIS SHEE | 4.23 | 4 | 94.49 | 100
7 | JHARGRAM | Sankrail | Jhargram Division | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House , & Providing Functional Household Tap Connection (2568 Nos), etc. For DUMRI NAKRASULI, JAKUA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000227/2022-2023 | 444/JHD | 23/03/2023 | 01/10/2025 | MASUM ALI KHAN | 772.82 | 183.53 | 23.75 | 65
8 | JHARGRAM | Sankrail | Central Drilling | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 19.51 | 0.09 | 11
Total | [13 empty] | 22160.18 | 207.04 | 0.93