## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS | SM/12349 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 422/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 33.76 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS | SM/12349 | New | Quotation for new service connection at Tikayetpur T/W-I water supply scheme. |  |  | BILL/00598/2024-2025 | 259/JMD | 15/07/2024 | 15/07/2024 | WBSEDCL | 6.86 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS | SM/12349 | New | New Service Connection Charges for Tikayetpur tw-I pwss |  |  | BILL/01200/2023-2024 | 41/JMD | 01/02/2024 | 01/02/2024 | WBSEDCL | 2.88 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-I | Jhargram Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS | SM/12349 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 101.54 | 0.83 | 25
5 | JHARGRAM | Gopiballavpur-I | Jhargram Division | TIAKITPUR ANAD AJOINING MOUJAS PWSS | SM/12349 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Tiakitpur and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000564/2023-2024 | 200/GPSD | 11/03/2024 | 10/04/2024 | DEBABRATA DUTTA | 4.3 | 3.63 | 84.43 | 5
Total | [13 empty] | 12332.56 | 105.17 | 0.85