## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | BANKATI AND IT'S ADJOINING MOUJAS | SM/12351 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1535/JHD | 06/09/2023 | 06/09/2023 | Resource Division | 70.86 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | BANKATI AND IT'S ADJOINING MOUJAS | SM/12351 | New | NEW SERVICE CONNECTION CHARGES FOR BANKATI T/W - II PWSS |  |  | BILL/01390/2023-2024 | 53/JMD | 12/03/2024 | 12/03/2024 | WBSEDCL | 5.32 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | BANKATI AND IT'S ADJOINING MOUJAS | SM/12351 | New | NEW SERVICE CONNECTION CHARGRES FOR BANKATI T/W -I PWSS |  |  | BILL/01389/2023-2024 | 52/JMD | 12/03/2024 | 12/03/2024 | WBSEDCL | 11.31 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Central Drilling | BANKATI AND IT'S ADJOINING MOUJAS | SM/12351 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | JHARGRAM | Binpur-I | Jhargram Division | BANKATI AND IT'S ADJOINING MOUJAS | SM/12351 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bankati and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000091/2024-2025 | 852/JSD | 03/09/2024 | 03/04/2025 | NAYAN CONSTRUCTION | 4.82 | 0 | 0 | 100
Total | [13 empty] | 21432.08 | 0 | 0