## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Petbindhi & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000048/2023-2024 | 1252/JMD | 26/05/2023 | 22/11/2023 | M/S B.M. ELECTRICAL | 22.09 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1595/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 42.7 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-II | Central Drilling | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000202/2023-2024 | 2104/CDD | 09/02/2024 | 09/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 110.72 | 19.91 | 17.98 | 10
4 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Soil Investigation and determination of safe bearing capacity and other relevant parameters of soil for construction of Proposed O.H.R. of Petbindhi and Dhadangiri PWSS at Gopiballavpur-II Block under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-III | ORD/000196/2024-2025 | 1086/JSD | 28/11/2024 | 12/12/2024 | MOYTEC | 1.34 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Quotation for new service connection at PETBINDHI TW-II watyer supply scheme. |  |  | BILL/00170/2024-2025 | 97/JMD | 08/05/2024 | 08/05/2024 | WBSEDCL | 5.02 | 0 | 0 | 0
6 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Quotation for new service connection at Petbindhi tw-I water supply scheme. |  |  | BILL/00176/2024-2025 | 103/JMD | 08/05/2024 | 08/05/2024 | WBSEDCL | 3.24 | 0 | 0 | 0
7 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Sinking of Tube Well , Pump House, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board & Accommodate FHTC(6721 nos) including 02(Two) Years Operation & Maintenance under JJM with allied work for DHADANGIRI, GOBINDAPUR, JUNSOLA, PETBINDHI & MAHAPAL PWSS in Gopiballavpur-II Block including supply of all labour & materials within Gopiballavpur Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000152/2023-2024 | 1373/JHD | 16/08/2023 | 23/11/2024 | M/S. EL-CON | 1574.44 | 0 | 0 | 0
8 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Petbindhi and its Adjoining Mouzas PWSS , Block: - Gopiballavpur-II, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-III | ORD/000099/2024-2025 | 857/JSD | 03/09/2024 | 03/10/2024 | MANAS DATTA | 4.79 | 0 | 0 | 100
9 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PETBINDHI AND ADJOINING MOUJAS PWSS | SM/12354 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Pet Bindhi GP at Gopiballavpur-II Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II,Junior Engineer-III | ORD/000426/2024-2025 | 1057/JSD | 22/11/2024 | 02/12/2024 | GOPAL JANA | 0.92 | 0 | 0 | 100
Total | [13 empty] | 1765.25 | 19.91 | 1.13