## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Constructions of 150 cum OHR, Installation of display Board, soil investigationunder JJM with allied work for PITHAPURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000187/2023-2024 | 1456/JHD | 30/08/2023 | 26/04/2024 | ABJ ENGINEERING | 73.26 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1554/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 37.24 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Laying distribution pipe line under JJM with allied work for PITHAPURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000198/2023-2024 | 1516/JHD | 05/09/2023 | 08/03/2025 | I R CONSTRUCTION | 87.13 | 0 | 0 | 85
4 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Sinking of Tube Well under JJM with allied work for PITHAPURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000208/2023-2024 | 1612/JHD | 08/09/2023 | 08/10/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.75 | 0 | 0 | 100
5 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Rising main pipe line, Interconnection pipe line, Accommodate FHTC ( 927 nos) under JJM with allied work for PITHAPURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000200/2023-2024 | 1564/JHD | 07/09/2023 | 05/06/2025 | I R CONSTRUCTION | 48.13 | 0 | 0 | 90
6 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Construction of Pump House under JJM with allied work for PITHAPURA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour and & materials within Jhargram Sub-Division. | Assistant Engineer | Junior Engineer-II | ORD/000326/2023-2024 | 1864/JHD | 01/11/2023 | 30/01/2024 | GANGULY ENTERPRISE | 12.24 | 0 | 0 | 100
7 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | New service connection charges |  |  | BILL/00874/2023-2024 | 47/JMD | 29/12/2023 | 29/12/2023 | WBSEDCL | 5.49 | 0 | 0 | 0
8 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Quotation for new servcie connection at PITHAPURA TW-II water supply scheme. |  |  | BILL/00168/2024-2025 | 95/JMD | 08/05/2024 | 08/05/2024 | WBSEDCL | 8.22 | 0 | 0 | 0
9 | JHARGRAM | Gopiballavpur-II | Central Drilling | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | JHARGRAM | Gopiballavpur-II | Jhargram Division | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kuliana GP at Gopiballavpur-II Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000424/2024-2025 | 1034/JSD | 13/11/2024 | 23/11/2024 | PRINT PREVIEW | 0.84 | 0 | 0 | 0
Total | [13 empty] | 21629.06 | 0 | 0