## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Constructions of 150 cum OHR, soil investigation under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000186/2023-2024 | 1455/JHD | 30/08/2023 | 26/04/2024 | ABJ ENGINEERING | 72.41 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Accommodate FHTC (382 nos) under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-10) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000358/2023-2024 | 2001/JHD | 01/12/2023 | 29/02/2024 | MAHAPRABHU ENTERPRISE | 16.13 | 0 | 0 | 0
3 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1570/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 57.74 | 0 | 0 | 0
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dalkati & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000040/2023-2024 | 1239/JMD | 26/05/2023 | 22/11/2023 | CHATTERJEE CONSTRUCTION | 20.81 | 4.54 | 21.79 | 60
5 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Laying distribution pipe line, Accommodate FHTC (383 nos) under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000158/2023-2024 | 1394/JHD | 18/08/2023 | 16/11/2023 | GOUTAM RAY | 79.26 | 59.77 | 75.41 | 90
6 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Dalkati and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000210/2024-2025 | 2292/JHD | 04/12/2024 | 03/01/2025 | TAPAS KUMAR HAZRA | 7.93 | 0 | 0 | 0
7 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Accommodate FHTC (383 nos) under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_35 of EE/JHD of 2022-23, SL No.-9, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-8) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000128/2024-2025 | 1134/JHD | 06/08/2024 | 04/11/2024 | RUPKUMAR KARMAKAR | 15.67 | 0 | 0 | 0
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | new meter connection charges of Dalkati-I water supply scheme |  |  | BILL/00017/2024-2025 | 16/JMD | 15/04/2024 | 15/04/2024 | WBSEDCL | 3.03 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | new meter connection charges of Dalkati T/W-II water supply scheme |  |  | BILL/00018/2024-2025 | 17/JMD | 15/04/2024 | 15/04/2024 | WBSEDCL | 9.97 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Sinking of Tube Well, Switch Room under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23,SL No.-8) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000324/2023-2024 | 1856/JHD | 31/10/2023 | 29/01/2024 | SHEFALI CONSTRUCTION | 29.03 | 23.27 | 80.16 | 95
11 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board under JJM with allied work for DALKATI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-7) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000396/2023-2024 | 3077/JHD | 26/12/2023 | 25/03/2024 | APEX ENGINEERING | 15.83 | 3.86 | 24.36 | 95
12 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Laying of distribution pipe line for Dalkati and its adjoining moujas pwss in Jhargram block within Jhargram district under jhargram division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000080/2024-2025 | 1213/JHD | 27/08/2024 | 11/10/2024 | RAMENDRA NATH KAR | 22.88 | 5.99 | 26.17 | 87
13 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Construction of boundary wall and Allied works At Dalkati 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000177/2024-2025 | 2194/JHD | 22/11/2024 | 21/01/2025 | SHEFALI CONSTRUCTION | 12.48 | 0 | 0 | 100
14 | JHARGRAM | Jhargram | Jhargram Division | DALKATI AND ADJOINING MOUJAS PWSS | SM/12357 | New | Trial run for DALKATI AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. (The date of starting of trial run will be effective after consultation with departmental officials) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000007/2025-2026 | 736/JHD | 02/04/2025 | 02/07/2025 | DHUMKETU ENGINEERING PRIVATE LIMITED | 1.01 | 0 | 0 | 0
Total | [13 empty] | 364.18 | 97.42 | 26.75