## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DARUKULI AND ADJOINING MOUJAS PWSS | SM/12358 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Darkuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000196/2023-2024 | 2111/JMD | 03/08/2023 | 30/01/2024 | S.K. ENTERPRISE | 15.64 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Central Drilling | DARUKULI AND ADJOINING MOUJAS PWSS | SM/12358 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Driller In Charge | Junior Engineer | ORD/000001/2024-2025 | 91/CDD | 25/04/2024 | 25/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 18.54 | 11.96 | 10
3 | JHARGRAM | Jhargram | Jhargram Division | DARUKULI AND ADJOINING MOUJAS PWSS | SM/12358 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DARUKULI AND ADJOINING MOUJAS PWSS | SM/12358 | New | NEW SERVICE CONNECTION CHARGES AT DORKULI-I WATER SUPPLY |  |  | BILL/01550/2024-2025 | 446/JMD | 09/01/2025 | 09/01/2025 | WBSEDCL | 7.62 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DARUKULI AND ADJOINING MOUJAS PWSS | SM/12358 | New | NEW SERVICE CONNECTION CHARGES AT DORKHULI-II WATER SUPPLY |  |  | BILL/01549/2024-2025 | 445/JMD | 09/01/2025 | 09/01/2025 | WBSEDCL | 3.06 | 0 | 0 | 0
Total | [13 empty] | 12466.1 | 18.54 | 0.15