## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Sankrail | Jhargram Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | SM/12359 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1504/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 34.35 | 0 | 0 | 0
2 | JHARGRAM | Sankrail | Jhargram Mechanical Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | SM/12359 | New | New service connection charges |  |  | BILL/00252/2023-2024 | 15/JMD/PFMS/APR | 27/07/2023 | 27/07/2023 | WBSEDCL | 2.89 | 0 | 0 | 0
3 | JHARGRAM | Sankrail | Jhargram Mechanical Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | SM/12359 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dumri Nakrasuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Driller-In-Charge | Junior Engineer | ORD/000203/2023-2024 | 2264/JMD | 09/08/2023 | 05/02/2024 | ORIENTAL ENGINEERING CO. | 22.08 | 9.39 | 42.53 | 55
4 | JHARGRAM | Sankrail | Jhargram Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | SM/12359 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House , & Providing Functional Household Tap Connection (2568 Nos), etc. For DUMRI NAKRASULI, JAKUA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000227/2022-2023 | 444/JHD | 23/03/2023 | 01/10/2025 | MASUM ALI KHAN | 772.82 | 336.46 | 43.54 | 65
5 | JHARGRAM | Sankrail | Jhargram Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | SM/12359 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Dumri Nekrasuli and its adjoining mouzas Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000354/2024-2025 | 134/GPSD | 18/03/2025 | 08/04/2025 | GOBINDA MAITY | 1.95 | 0 | 0 | 100
6 | JHARGRAM | Sankrail | Jhargram Mechanical Division | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | SM/12359 | New | WBSEDCL Quotation bill of Dumri-Nekrasuli w/s scheme, t/w no.II |  |  | BILL/00921/2025-2026 |  | 22/08/2025 | 22/08/2025 | WBSEDCL | 5.52 | 0 | 0 | 0
7 | JHARGRAM | Sankrail | Central Drilling | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | SM/12359 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22179.37 | 345.85 | 1.56