## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | SM/12386 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mahapal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000073/2023-2024 | 1254/JMD | 26/05/2023 | 22/11/2023 | SUBHASIS ROY | 22.71 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-II | Jhargram Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | SM/12386 | New | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 1547/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 18.97 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-II | Central Drilling | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | SM/12386 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000202/2023-2024 | 2104/CDD | 09/02/2024 | 09/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 110.72 | 19.23 | 17.37 | 10
4 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | SM/12386 | New | Quotation for new service connection at Mahapal tw-I water supply scheme. |  |  | BILL/00349/2024-2025 | 152/JMD | 31/05/2024 | 31/05/2024 | WBSEDCL | 3.42 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | SM/12386 | New | Quotation for new service connection at Mahapal tw-II water supply scheme. |  |  | BILL/00348/2024-2025 | 151/JMD | 31/05/2024 | 31/05/2024 | WBSEDCL | 3.6 | 0 | 0 | 0
6 | JHARGRAM | Gopiballavpur-II | Jhargram Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | SM/12386 | New | Sinking of Tube Well , Pump House, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board & Accommodate FHTC(6721 nos) including 02(Two) Years Operation & Maintenance under JJM with allied work for DHADANGIRI, GOBINDAPUR, JUNSOLA, PETBINDHI & MAHAPAL PWSS in Gopiballavpur-II Block including supply of all labour & materials within Gopiballavpur Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000152/2023-2024 | 1373/JHD | 16/08/2023 | 23/11/2024 | M/S. EL-CON | 1574.44 | 0 | 0 | 0
7 | JHARGRAM | Gopiballavpur-II | Jhargram Division | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | SM/12386 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Mahapal and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division,Junior Engineer-III | ORD/000065/2024-2025 | 790/JSD | 09/08/2024 | 08/09/2024 | DEEPSHIKHA ENTERPRISE | 4.68 | 0 | 0 | 90
Total | [13 empty] | 1738.53 | 19.23 | 1.11