## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Central Drilling | CHAMPASOL AND ADJOINING MOUJAS PWSS | SM/12387 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 26.41 | 0.12 | 11
2 | JHARGRAM | Jhargram | Jhargram Division | CHAMPASOL AND ADJOINING MOUJAS PWSS | SM/12387 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 124.38 | 1.01 | 25
3 | JHARGRAM | Jhargram | Jhargram Division | CHAMPASOL AND ADJOINING MOUJAS PWSS | SM/12387 | New | Construction of boundary wall and Allied works At Dahatmal,Bagmuri,Champasol 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000097/2024-2025 | 1280/JHD | 03/09/2024 | 03/10/2024 | PROVAT KUMAR DE | 37.25 | 8.28 | 22.22 | 30
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHAMPASOL AND ADJOINING MOUJAS PWSS | SM/12387 | New | New service connection charges at Champasole water supply scheme |  |  | BILL/00402/2024-2025 | 191/JMD | 14/06/2024 | 14/06/2024 | WBSEDCL | 11.57 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHAMPASOL AND ADJOINING MOUJAS PWSS | SM/12387 | New | NEW SERVICE CONNECTION CHARGES AT CHAMPASOLE-2 PWSS |  |  | BILL/00918/2025-2026 |  | 22/08/2025 | 22/08/2025 | WBSEDCL | 4.41 | 0 | 0 | 0
Total | [13 empty] | 33677.77 | 159.07 | 0.47