## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Bhalukasol and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-III | ORD/000556/2023-2024 | 192/GPSD | 11/03/2024 | 10/04/2024 | GOPESH DEY | 4.03 | 0 | 0 | 98
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 424/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 45.06 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Quotation for new service connection at BHALUKASOLE T/W-II water supply scheme. |  |  | BILL/00013/2024-2025 | 13/JMD | 05/04/2024 | 05/04/2024 | WBSEDCL | 2.56 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | New Service connection charges |  |  | BILL/01193/2023-2024 | 34/JMD | 01/02/2024 | 01/02/2024 | WBSEDCL | 4.62 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-I | Central Drilling | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
7 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Patina GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000234/2024-2025 | 647/GPSD | 19/11/2024 | 29/11/2024 | PRINT PREVIEW | 0.92 | 0 | 0 | 100
Total | [13 empty] | 33681.72 | 0 | 0