## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Bhalukasol and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-III | ORD/000556/2023-2024 | 192/GPSD | 11/03/2024 | 10/04/2024 | GOPESH DEY | 4.03 | 4.03 | 99.94 | 98
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 424/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 45.06 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Quotation for new service connection at BHALUKASOLE T/W-II water supply scheme. |  |  | BILL/00013/2024-2025 | 13/JMD | 05/04/2024 | 05/04/2024 | WBSEDCL | 2.56 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | New Service connection charges |  |  | BILL/01193/2023-2024 | 34/JMD | 01/02/2024 | 01/02/2024 | WBSEDCL | 4.62 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 314.57 | 2.56 | 25
6 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Patina GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000234/2024-2025 | 647/GPSD | 19/11/2024 | 29/11/2024 | PRINT PREVIEW | 0.92 | 0.91 | 98.82 | 100
7 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Baligeria, Chandrarekha GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000227/2024-2025 | 640/GPSD | 19/11/2024 | 29/11/2024 | GOPAL JANA | 0.59 | 0.58 | 98.82 | 100
8 | JHARGRAM | Gopiballavpur-I | Central Drilling | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 40.17 | 0.19 | 11
9 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data ith the objective of controlling multiple entry, improving data quality in terms of absolute household by erification through electric connection any other unique documents and making error free in Afferent Pipe Water Supply Scheme In different Block in the District of Jhargram under Jhargram Division. PHE Dte.(130-Bhalukasol PWSS within Gopiballavpur-I Block) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000267/2024-2025 | 362/GPSD | 08/04/2024 | 05/09/2024 | TECHVISION | 0.5 | 0 | 0 | 50
Total | [13 empty] | 33682.81 | 360.25 | 1.07