## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of GHORA PINCHA & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-I Block, District: - Jhargram. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000385/2023-2024 | 2056/JHD | 07/12/2023 | 04/07/2024 | ASIS KUMAR SARANGI | 73.5 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1579/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 25.64 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Pump House, 100 cum GLR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Accommodate FHTC (929 nos) under JJM with allied work for GHORAPINCHA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000067/2023-2024 | 1097/JHD | 14/07/2023 | 10/01/2024 | ASIS KUMAR SARANGI | 87.33 | 30.01 | 34.37 | 90
4 | JHARGRAM | Gopiballavpur-I | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Sinking of Tube Well, Pump House under JJM with allied work for GHORAPINCHA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000081/2023-2024 | 1119/JHD | 19/07/2023 | 17/10/2023 | ASIS KUMAR SARANGI | 29.33 | 23.15 | 78.93 | 95
5 | JHARGRAM | Gopiballavpur-I | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Laying distribution pipe line under JJM with allied work for GHORAPINCHA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000140/2023-2024 | 1327/JHD | 10/08/2023 | 17/12/2024 | ASIS KUMAR SARANGI | 123.65 | 89.68 | 72.53 | 96
6 | JHARGRAM | Gopiballavpur-I | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Supplying and Delivery of Different dia CIDF Sluice Valve,CIDF Pipes & Specials etc for Laying distribution of HDPE Pipe Line and Inter Connection between Tube Well and Rising main & OHR including By-Pass arrangement etc. For Ghorapincha & its Adjoining Mouzas PWSS in Gopiballavpur-I Block under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000198/2024-2025 | 684/GPSD | 02/12/2024 | 23/12/2024 | ASSOCIATED ENGINEERS & TRADERS | 3.57 | 0 | 0 | 0
7 | JHARGRAM | Gopiballavpur-I | Jhargram Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Ghorapincha and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-III | ORD/000561/2023-2024 | 197/GPSD | 11/03/2024 | 10/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 4.3 | 4.28 | 99.59 | 100
8 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Quotation for new service connection at Ghorapitcha T/W-II water supply scheme. |  |  | BILL/00519/2024-2025 | 236/JMD | 09/07/2024 | 09/07/2024 | WBSEDCL | 3.04 | 0 | 0 | 0
9 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Quotation for new service connection at Ghorapitcha T/W-I water supply scheme. |  |  | BILL/00518/2024-2025 | 235/JMD | 09/07/2024 | 09/07/2024 | WBSEDCL | 7.07 | 0 | 0 | 0
10 | JHARGRAM | Gopiballavpur-I | Central Drilling | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 17.44 | 0.08 | 11
Total | [13 empty] | 21697.2 | 164.56 | 0.76