## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Sankrail | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1500/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 104.12 | 0 | 0 | 0
2 | JHARGRAM | Sankrail | Jhargram Mechanical Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | New Service connection |  |  | BILL/00657/2023-2024 | 8/JMD | 08/11/2023 | 08/11/2023 | WBSEDCL | 2.97 | 0 | 0 | 0
3 | JHARGRAM | Sankrail | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of HARIPURBIRUA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000470/2023-2024 | 165/GPSD | 05/03/2024 | 04/04/2024 | FIROJ KHAN | 4.14 | 0 | 0 | 100
4 | JHARGRAM | Sankrail | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | Continuation work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for 16th March 2024 to 31st March 2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000698/2023-2024 | 473/JRWS | 13/03/2024 | 29/03/2024 | JAGOMOHAN SETUA | 0.53 | 0 | 0 | 100
5 | JHARGRAM | Sankrail | Jhargram Mechanical Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | New service connection charges for Haripurbirua, t/w no.II pwss |  |  | BILL/01369/2023-2024 | 32/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.1 | 0 | 0 | 0
6 | JHARGRAM | Sankrail | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system ,Pump House ,& Providing Functional Household Tap Connection (7650 Nos), etc. For BAKRA, GOBINDAPUR, HARIPURBIRUA, KARKATASOL, Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000226/2022-2023 | 443/JHD | 23/03/2023 | 01/10/2025 | GOBINDA MAITY | 2154.34 | 0 | 0 | 70
7 | JHARGRAM | Sankrail | Central Drilling | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | JHARGRAM | Sankrail | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection with By-Pass arrangement for Haripurbirua and its adjoining mouzas Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000353/2024-2025 | 133/GPSD | 18/03/2025 | 08/04/2025 | GOBINDA MAITY | 2.2 | 0 | 0 | 100
9 | JHARGRAM | Sankrail | Jhargram Division | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chandabila GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000230/2024-2025 | 643/GPSD | 19/11/2024 | 29/11/2024 | GOPAL JANA | 0.92 | 0 | 0 | 100
Total | [13 empty] | 23612.08 | 0 | 0