## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Mechanical Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | New Service connection |  |  | BILL/00666/2023-2024 | 14/JMD | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.16 | 0 | 0 | 0
2 | JHARGRAM | Jamboni | Jhargram Mechanical Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | New Service connection |  |  | BILL/00410/2023-2024 | 5/JMD | 07/09/2023 | 07/09/2023 | WBSEDCL | 3.32 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 427/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 7.15 | 0 | 0 | 0
4 | JHARGRAM | Jamboni | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | JHARGRAM | Jamboni | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House,& Providing Functional Household Tap Connection (1685 Nos) including 02(Two) Years Operation & Maintenance For CHANDABILE , TULIBAR Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000090/2023-2024 | 1138/JHD | 20/07/2023 | 30/06/2025 | ASIS KUMAR SARANGI | 629.25 | 0 | 0 | 95
6 | JHARGRAM | Jamboni | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Belia and Chandabila PWSS , Block Jamboni, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-III | ORD/000330/2024-2025 | 503/JHD | 07/03/2025 | 06/05/2025 | M/S DURGA ENTERPRISE | 28.11 | 0 | 0 | 0
7 | JHARGRAM | Jamboni | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 23/S&WSD | 29/01/2025 | 01/08/2025 | SULEKHA GHOSH | 0.87 | 0 | 0 | 0
8 | JHARGRAM | Jamboni | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000037/2025-2026 | 154/S&WSD | 29/07/2025 | 29/01/2026 | SULEKHA GHOSH | 0.87 | 0 | 0 | 0
Total | [13 empty] | 22012.51 | 0 | 0