## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Mechanical Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | New Service connection |  |  | BILL/00666/2023-2024 | 14/JMD | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.16 | 0 | 0 | 0
2 | JHARGRAM | Jamboni | Jhargram Mechanical Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | New Service connection |  |  | BILL/00410/2023-2024 | 5/JMD | 07/09/2023 | 07/09/2023 | WBSEDCL | 3.32 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 427/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 7.15 | 0 | 0 | 0
4 | JHARGRAM | Jamboni | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | JHARGRAM | Jamboni | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House,& Providing Functional Household Tap Connection (1685 Nos) including 02(Two) Years Operation & Maintenance For CHANDABILE , TULIBAR Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000090/2023-2024 | 1138/JHD | 20/07/2023 | 30/06/2025 | ASIS KUMAR SARANGI | 629.25 | 0 | 0 | 95
6 | JHARGRAM | Jamboni | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Belia and Chandabila PWSS , Block Jamboni, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-III | ORD/000330/2024-2025 | 503/JHD | 07/03/2025 | 06/05/2025 | M/S DURGA ENTERPRISE | 28.11 | 0 | 0 | 0
7 | JHARGRAM | Jamboni | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 23/S&WSD | 29/01/2025 | 01/08/2025 | SULEKHA GHOSH | 0.87 | 0 | 0 | 0
8 | JHARGRAM | Jamboni | Central Drilling | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000037/2025-2026 | 154/S&WSD | 29/07/2025 | 29/01/2026 | SULEKHA GHOSH | 0.87 | 0 | 0 | 0
9 | JHARGRAM | Jamboni | Jhargram Division | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Chandabila and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division,Junior Engineer-III | ORD/000589/2023-2024 | 528/JRWS | 16/03/2024 | 15/05/2024 | ASSOCIATED ENGINEERS & TRADERS | 4.84 | 0 | 0 | 70
Total | [13 empty] | 22017.35 | 0 | 0