## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | HARDA AND ADJOINING MOUJAS PWSS | SM/12436 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1538/JHD | 06/09/2023 | 06/09/2023 | Resource Division | 63.14 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | HARDA AND ADJOINING MOUJAS PWSS | SM/12436 | New | Quotation for new cesvice connection at Harda tw-1 water supply scheme. |  |  | BILL/01503/2023-2024 | 93/JMD | 22/03/2024 | 22/03/2024 | WBSEDCL | 11.49 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | HARDA AND ADJOINING MOUJAS PWSS | SM/12436 | New | New service connection charges |  |  | BILL/00875/2023-2024 | 48/JMD | 29/12/2023 | 29/12/2023 | WBSEDCL | 3.67 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Central Drilling | HARDA AND ADJOINING MOUJAS PWSS | SM/12436 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21418.06 | 0 | 0