## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Division | DOMAHANI AND ADJOINING MOUJAS PWSS | SM/12438 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (1160 nos) under JJM with allied work for Domahani PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000217/2022-2023 | 347/JHD | 10/03/2023 | 06/09/2023 | ASIS KUMAR SARANGI | 387.03 | 0 | 0 | 0
2 | JHARGRAM | Jamboni | Jhargram Division | DOMAHANI AND ADJOINING MOUJAS PWSS | SM/12438 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1604/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 13.75 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Division | DOMAHANI AND ADJOINING MOUJAS PWSS | SM/12438 | New | Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_4_A under Jhargram Division in the District of Jhargram. | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000068/2022-2023 | 347/JHD | 28/09/2022 | 26/01/2023 | M/S. SANKAR KUMAR NAG | 22.33 | 2.8 | 12.54 | 100
4 | JHARGRAM | Jamboni | Jhargram Division | DOMAHANI AND ADJOINING MOUJAS PWSS | SM/12438 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kapgari GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-III | ORD/000248/2024-2025 | 370/JRWS | 04/10/2024 | 14/10/2024 | MANOJ KUMAR MAHATA | 0.67 | 0 | 0 | 100
5 | JHARGRAM | Jamboni | Central Drilling | DOMAHANI AND ADJOINING MOUJAS PWSS | SM/12438 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 10.51 | 0.05 | 11
Total | [13 empty] | 21763.55 | 13.31 | 0.06