## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1551/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 29.71 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | New Service connection |  |  | BILL/00660/2023-2024 | 11/JMD | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.25 | 0 | 0 | 0
3 | JHARGRAM | Jhargram | Jhargram Mechanical Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | New Service connection |  |  | BILL/00659/2023-2024 | 10/JMD | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.12 | 0 | 0 | 0
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Murabani & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000069/2023-2024 | 1240/JMD | 26/05/2023 | 22/11/2023 | R.K. ENTERPRISES | 20.82 | 0 | 0 | 60
5 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Laying of Distribution pipe line for MURABANI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-I | ORD/000059/2023-2024 | 1094/JHD | 14/07/2023 | 12/10/2023 | SAIKAT DANDAPAT | 61.33 | 0 | 0 | 30
6 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Accommodate FHTC ( 1316 nos) under JJM with allied work for MURABANI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division,Junior Engineer-I | ORD/000060/2023-2024 | 1095/JHD | 14/07/2023 | 12/10/2023 | SAIKAT DANDAPAT | 55.48 | 0 | 0 | 20
7 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Murabani and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000103/2024-2025 | 1314/JHD | 05/09/2024 | 05/10/2024 | HONEY CONSTRUCTION | 3.71 | 0 | 0 | 0
8 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Schedule for Construction of Boundary wall and allied works at 1st. Tube well site of Murabani and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000178/2024-2025 | 2193/JHD | 22/11/2024 | 22/12/2024 | MANDAL ENTERPRISE | 8.07 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Switch room cum chlorine room at different pipe water supply scheme for MURABONI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block under Jhargrm Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block,Junior Engineer-I | ORD/000577/2023-2024 | 437/JHD | 14/03/2024 | 28/04/2024 | MANDAL ENTERPRISE | 6.02 | 0 | 0 | 100
10 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Sinking of Tube Well , Laying distribution pipe line, under JJM with allied work for MURABANI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_15 of 2022-23 , SL No.-2 ) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000131/2023-2024 | 1340/JHD | 10/08/2023 | 08/11/2023 | BIDYUT KUMAR SANTRA | 93.89 | 0 | 0 | 90
11 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Construction of Pump House , 150 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , under JJM with allied work for MURABANI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_15 of 2022-23 , SL No.-1 ) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000172/2023-2024 | 1424/JHD | 23/08/2023 | 20/03/2024 | SUBRATA DAS | 90.46 | 0 | 0 | 60
12 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Trial run for MURABANI AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000001/2025-2026 | 730/JHD | 02/04/2025 | 02/07/2025 | DHUMKETU ENGINEERING PRIVATE LIMITED | 1.09 | 0 | 0 | 0
13 | JHARGRAM | Jhargram | Jhargram Division | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Murabani and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000187/2024-2025 | 2191/JHD | 22/11/2024 | 22/12/2024 | S.B.TRADERS | 8.31 | 0 | 0 | 90
Total | [13 empty] | 385.27 | 0 | 0