## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Mechanical Division | BAHIR GRAM AND ADJOINING MOUJAS PWSS | SM/12441 | New | New Service Connection |  |  | BILL/00384/2023-2024 | 23/AUG | 25/08/2023 | 25/08/2023 | WBSEDCL | 7.91 | 0 | 0 | 0
2 | JHARGRAM | Jamboni | Jhargram Mechanical Division | BAHIR GRAM AND ADJOINING MOUJAS PWSS | SM/12441 | New | New service connection |  |  | BILL/00385/2023-2024 | 24/AUG | 25/08/2023 | 25/08/2023 | WBSEDCL | 2.81 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Central Drilling | BAHIR GRAM AND ADJOINING MOUJAS PWSS | SM/12441 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 31.5 | 0.15 | 11
4 | JHARGRAM | Jamboni | Jhargram Division | BAHIR GRAM AND ADJOINING MOUJAS PWSS | SM/12441 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection ( 7683 Nos), etc.including 02(Two) Years Operation & Maintenance For KAMTA , SUSHNI, BAHIR GRAM, KAPGARI, MURAKATI, MAHISAMURA PWSS Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000353/2023-2024 | 1954/JHD | 22/11/2023 | 01/01/2025 | SIBSANKAR CHOWDHURY | 2070.24 | 56.61 | 2.73 | 65
Total | [13 empty] | 23420.73 | 88.11 | 0.38