## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , Accommodate FHTC ( 1424 nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for BELIA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000017/2023-2024 | 789/JHD | 31/05/2023 | 30/05/2025 | ASIS KUMAR SARANGI | 353.43 | 198.14 | 56.06 | 80
2 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Belia & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000205/2023-2024 | 2266/JMD | 09/08/2023 | 05/02/2024 | CHAKRABORTY MINING & ENGINEERING | 22.09 | 18.06 | 81.75 | 65
3 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1545/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 31.34 | 0 | 0 | 0
4 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | New service connection |  |  | BILL/00386/2023-2024 | 25/AUG | 25/08/2023 | 25/08/2023 | WBSEDCL | 5.64 | 0 | 0 | 0
5 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | New service connection |  |  | BILL/00339/2023-2024 | 18/AUG | 24/08/2023 | 24/08/2023 | WBSEDCL | 2.94 | 0 | 0 | 0
6 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Belia and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division,Junior Engineer-III | ORD/000581/2023-2024 | 516/JRWS | 15/03/2024 | 14/05/2024 | MANDAL ENTERPRISE | 4.77 | 0 | 0 | 90
7 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Gidhni GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-III | ORD/000246/2024-2025 | 362/JRWS | 01/10/2024 | 11/10/2024 | GOPAL JANA | 0.92 | 0 | 0 | 100
8 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Belia and Chandabila PWSS , Block Jamboni, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-III | ORD/000330/2024-2025 | 503/JHD | 07/03/2025 | 06/05/2025 | M/S DURGA ENTERPRISE | 28.11 | 0 | 0 | 0
Total | [13 empty] | 449.24 | 216.21 | 48.13