## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1545/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 31.34 | 0 | 0 | 0
2 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | New service connection |  |  | BILL/00386/2023-2024 | 25/AUG | 25/08/2023 | 25/08/2023 | WBSEDCL | 5.64 | 0 | 0 | 0
3 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | New service connection |  |  | BILL/00339/2023-2024 | 18/AUG | 24/08/2023 | 24/08/2023 | WBSEDCL | 2.94 | 0 | 0 | 0
4 | JHARGRAM | Jamboni,Jhargram | Jhargram Mechanical Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Belia & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000205/2023-2024 | 2266/JMD | 09/08/2023 | 05/02/2024 | CHAKRABORTY MINING & ENGINEERING | 22.09 | 0 | 0 | 65
5 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , Accommodate FHTC ( 1424 nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for BELIA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000017/2023-2024 | 789/JHD | 31/05/2023 | 27/11/2023 | ASIS KUMAR SARANGI | 353.43 | 0 | 0 | 80
6 | JHARGRAM | Jamboni,Jhargram | Jhargram Division | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Belia and Chandabila PWSS , Block Jamboni, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-III | ORD/000330/2024-2025 | 503/JHD | 07/03/2025 | 06/05/2025 | M/S DURGA ENTERPRISE | 28.11 | 0 | 0 | 0
Total | [13 empty] | 443.55 | 0 | 0