## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1600/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 34.47 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chenchur Geria & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000043/2023-2024 | 1246/JMD | 26/05/2023 | 22/11/2023 | M/S. SAMRIDDHI ENTERPRISE | 21.88 | 16.2 | 74.02 | 50
3 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Construction of Laying distribution pipe line under JJM with allied work for CHENCHUR GERYA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000020/2023-2024 | 790/JHD | 31/05/2023 | 29/08/2023 | PROVAT KUMAR DE | 69.24 | 66.22 | 95.64 | 100
4 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Chenchur Geriya and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000217/2024-2025 | 2411/JHD | 12/12/2024 | 11/01/2025 | K.D.CONSTRUCTION | 8.17 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Supplying and Delivery of Different Dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Chenchur Gerya and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000207/2024-2025 | 2295/JHD | 04/12/2024 | 03/01/2025 | BIKASH MANDAL | 7.92 | 0 | 0 | 0
6 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chandri GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000113/2024-2025 | 1839/JHD | 20/09/2024 | 30/09/2024 | GOPAL JANA | 0.75 | 0.75 | 100 | 100
7 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chubka GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000114/2024-2025 | 1840/JHD | 20/09/2024 | 30/09/2024 | PRINT PREVIEW | 0.59 | 0.59 | 100 | 100
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | new service connection charges at Chenchurgerya water supply scheme |  |  | BILL/00233/2024-2025 | 114/JMD | 13/05/2024 | 13/05/2024 | WBSEDCL | 8.71 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Accommodate FHTC ( 1553 nos) under JJM with allied work for CHENCHUR GERYA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block,Junior Engineer-III | ORD/000021/2023-2024 | 791/JHD | 31/05/2023 | 29/08/2023 | PROVAT KUMAR DE | 65.48 | 22.62 | 34.54 | 90
10 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Construction of Laying distribution pipe line under JJM with allied work for CHENCHUR GERYA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000136/2023-2024 | 1317/JHD | 10/08/2023 | 08/11/2023 | RAMENDRA NATH KAR | 43.66 | 35.91 | 82.26 | 90
11 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Sinking of Tube Well , Pump House , 250 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation under JJM with allied work for CHENCHUR GERYA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_19 of 2022-23 , SL No.-1 ) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000204/2023-2024 | 1515/JHD | 05/09/2023 | 02/04/2024 | SATYANARAYAN BISWAS | 205.51 | 106.41 | 51.78 | 80
12 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Sinking of Tube Well , Interconnection pipe line, Laying distribution pipe line, under JJM with allied work for CHENCHUR GERYAAND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_19 of 2022-23 , SL No.-4 ) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block,Junior Engineer-III | ORD/000128/2023-2024 | 1343/JHD | 10/08/2023 | 08/11/2023 | NIMAI LAL GURIA | 18.79 | 17.5 | 93.15 | 100
13 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Chenchur Geriya and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000124/2024-2025 | 1316/JHD | 05/09/2024 | 05/10/2024 | KAUSTAV SARKAR | 3.75 | 0 | 0 | 85
14 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | Trial run for CHENCHUR GERYA AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. (Effected from 01/09/2025) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000006/2025-2026 | 735/JHD | 02/04/2025 | 02/07/2025 | SANDIP GURIA | 1.22 | 0 | 0 | 100
15 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | M.S./GI Fabricated Structure & G.l Casing Pipe for Canal crossing Of water Supply Pipe Line AT CHENCHURGERIYA AND ADJOINING MOUZAS PWSS WITHIN JHARGRAM BLOCK UNDER JHARGRAM DIVISION, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000400/2024-2025 | 284/JHD | 07/02/2025 | 09/03/2025 | PROVAT KUMAR DE | 0.89 | 0 | 0 | 100
16 | JHARGRAM | Jhargram | Jhargram Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | GI pipe at culvert crossing over mini canal at CHENCHURGERIYA and adjoining mouzas PWSS within Jhargram block under Jhargram division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000401/2024-2025 | 273/JHD | 06/02/2025 | 08/03/2025 | NIMAI LAL GURIA | 0.57 | 0 | 0 | 100
17 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 | New | new service connection charges at Chenchurgeria-2 water supply scheme |  |  | BILL/01614/2024-2025 | 465/JMD | 21/01/2025 | 21/01/2025 | WBSEDCL | 6.12 | 0 | 0 | 0
Total | [13 empty] | 497.73 | 266.21 | 53.48