## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12449 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1589/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 70.94 | 0 | 0 | 0
2 | JHARGRAM | Jamboni | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12449 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House& Providing Functional Household Tap Connection (2163 Nos), including 02(Two)Years Operation & Maintanance For KHAMARPARA, TENTULIA Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000111/2023-2024 | 1207/JHD | 26/07/2023 | 22/07/2025 | SUNIL DULE | 651.28 | 10.46 | 1.61 | 70
Total | [13 empty] | 722.23 | 10.46 | 1.45