## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Mechanical Division | PINDRAKULI AND ADJOINING MOUJAS PWSS | SM/12450 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pindra Kuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000032/2023-2024 | 1230/JMD | 26/05/2023 | 22/11/2023 | RSA ENTERPRISE | 20.71 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Central Drilling | PINDRAKULI AND ADJOINING MOUJAS PWSS | SM/12450 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Driller In Charge | Junior Engineer | ORD/000001/2024-2025 | 91/CDD | 25/04/2024 | 25/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
3 | JHARGRAM | Jhargram | Jhargram Division | PINDRAKULI AND ADJOINING MOUJAS PWSS | SM/12450 | New | Construction of Pump House , 100 cum OHR & 250 Cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Soil investigation & Accommodate FHTC (3051 nos) under JJM with allied work including 02(Two) Years Operation & Maintanance for RAJBAND, PINDRAKULI & RAJABASA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000380/2024-2025 | 667/JHD | 26/03/2025 | 22/09/2025 | ASIS KUMAR SARANGI | 813.53 | 0 | 0 | 0
Total | [13 empty] | 989.25 | 0 | 0