## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Sinking of Tube Well under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-1) | Assistant Engineer | Junior Engineer-III | ORD/000046/2024-2025 | 1137/JHD | 06/08/2024 | 05/09/2024 | PALASH MANDAL | 16.67 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Constructions of Pump House under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_35 of EE/JHD of 2022-23, SL No.-2, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-3) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000568/2023-2024 | 435/JHD | 14/03/2024 | 12/06/2024 | MILON MAITY | 12.39 | 10.6 | 85.55 | 10
3 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Supply & Delivery of CI&DI Specials for laying of Rising Main including interconnection between Tube Well and Raising Main and OHR for Bhila and its adjoining mouzas Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000199/2024-2025 | 685/GPSD | 02/12/2024 | 23/12/2024 | A R CONSTRUCTION | 2.31 | 0.51 | 21.91 | 95
4 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 426/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 20.49 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Quotation for Bhila T/W - I water supply scheme. |  |  | BILL/01424/2023-2024 | 73/JMD | 15/03/2024 | 15/03/2024 | WBSEDCL | 2.86 | 0 | 0 | 0
6 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Quotation for Bhila T/W - 2 water supply scheme. |  |  | BILL/01425/2023-2024 | 74/JMD | 15/03/2024 | 15/03/2024 | WBSEDCL | 3.96 | 0 | 0 | 0
7 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Laying distribution pipe line under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000323/2023-2024 | 1857/JHD | 31/10/2023 | 28/04/2024 | ONKAR ENTERPRISE | 174.38 | 139.21 | 79.83 | 95
8 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Rising main pipe line, Interconnection pipe line, Laying of Distribution pipe line, Installation of display Board, FHTC I 497 under JJM with allied work for BHILA AND IT'S ADJOINING I MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT 35 of 2022-23, SL No.-4) | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000330/2023-2024 | 1865/JHD | 01/11/2023 | 30/01/2024 | R.CONSTRUCTION | 59.84 | 39 | 65.18 | 95
9 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Supplying and Delivery of Different dia CIDF Sluice Valve, including Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Bhila & its Adjoining Mouzas PWSS in Gopiballavpur-I Block under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-I block,Junior Engineer-III | ORD/000254/2024-2025 | 42/JHD | 07/01/2025 | 21/02/2025 | ONKAR ENTERPRISE | 8.34 | 0 | 0 | 45
10 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bhila, Gohalbura and Barasol and its adjoining Mouzas , Block Gopiballavpur-I, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-III | ORD/000299/2024-2025 | 313/JHD | 12/02/2025 | 13/04/2025 | ANUSKA ENTERPRISE | 43.87 | 0 | 0 | 0
11 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Constructions of 150 cum OHR, soil investigation under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000278/2023-2024 | 1653/JHD | 15/09/2023 | 12/05/2024 | KANAN CONSTRUCTION ENTERPRISE | 73.16 | 24.16 | 33.03 | 95
12 | JHARGRAM | Gopiballavpur-I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Bhila and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000565/2023-2024 | 201/GPSD | 11/03/2024 | 10/04/2024 | J.S.S. ENTERPRISE | 4.3 | 1.45 | 33.64 | 10
Total | [13 empty] | 422.56 | 214.93 | 50.86