## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 1561/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 64.65 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for April-2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000699/2023-2024 | 572/JRWS | 28/03/2024 | 27/04/2024 | JAGOMOHAN SETUA | 0.53 | 0.5 | 95.48 | 100
3 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | New service connection charges |  |  | BILL/00876/2023-2024 | 49/JMD | 29/12/2023 | 29/12/2023 | WBSEDCL | 4.78 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | New Service connection charges. |  |  | BILL/01479/2023-2024 | 84/JMD | 21/03/2024 | 21/03/2024 | WBSEDCL | 5.52 | 0 | 0 | 0
5 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | Quotation for new service connection at Thakurpara TW-III water supply scheme. |  |  | BILL/00390/2024-2025 | 186/JMD | 11/06/2024 | 11/06/2024 | WBSEDCL | 6.61 | 0 | 0 | 0
6 | JHARGRAM | Binpur-I,Binpur-II | Central Drilling | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 57.73 | 0.27 | 11
7 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (24693) including 02(Two) Years Operation & Maintenance For 14 Nos Pipe water supply Scheme within BINPUR-I Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000069/2023-2024 | 1113/JHD | 18/07/2023 | 27/03/2026 | M/S SWACH ENVIRONMENT PRIVATE LTD. | 7215.68 | 262.75 | 3.64 | 55
8 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | Construction of Boundary wall allied works at 2nd Tube well site for Proposed Pipe Water Supply Scheme of Thakurpara and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram Under Jhargram Division ,PHE Dte. Total length 50 mtr,column size 25x250mm,3.00 M c/c ht 2.300mtr from G.L(Type -B) | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000049/2024-2025 | 765/JSD | 09/08/2024 | 05/04/2025 | ASHIS SHEE | 4.78 | 0 | 0 | 100
9 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 | New | Construction of Boundary wall & allied works at 3rd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Thakurpara and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr, column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) (2nd Call) [Ref. eNIT 20 OF AE/JSD OF 2023-2024, SL No. 15] | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000141/2024-2025 | 970/JSD | 01/10/2024 | 29/01/2025 | ASHIS SHEE | 4.51 | 0 | 0 | 100
Total | [13 empty] | 28646.82 | 320.98 | 1.12